## Tasks
Task | Owner | Status | Due | Priority | Notes | Category
Venue
Book main hall - TEST 22 | Sarah Kim | Done | 2026-02-15 | High | Signed contract with Marriott Bay. Deposit paid. | Venue
Site visit | Sarah Kim | Done | 2026-02-20 | High | Walkthrough completed with venue coordinator. | Venue
Confirm parking | Sarah Kim | Done | 2026-03-01 | High | Main lot holds 180 cars. Overflow lot secured across street (120 additional spots). | Venue
AV walkthrough | Mike Chen | Done | 2026-03-08 | High | Completed with venue AV team. All equipment verified. | Venue
Signage quotes | Alex Johnson | Done | 2026-03-05 | Medium | Selected SignWorks. 12 banners plus directional signage ordered. | Venue
Furniture rental | Alex Johnson | Done | 2026-03-07 | Low | 200 chairs and 30 cocktail tables from EventPro. | Venue
Catering menu tasting | Sarah Kim | Done | 2026-02-25 | Medium | Option B (Mediterranean). Vegetarian track confirmed. | Venue
Confirm headcount with catering | Sarah Kim | In Progress | 2026-03-14 | High | Final count due 7 days prior to event. | Venue
Speakers
Lock keynote | Sarah Kim | Done | 2026-01-30 | High | Alicia Wu confirmed. Rider received 2026-03-01. | Speakers
Speaker contracts (8) | Jenny Lee | Done | 2026-02-28 | High | All 8 contracts signed and returned. | Speakers
Travel arrangements | Jenny Lee | In Progress | 2026-03-15 | Medium | Using TravelCo portal. Budget $2000 per speaker (flight and hotel). | Speakers
Bios and headshots | Jenny Lee | Done | 2026-02-20 | Medium | All 8 bios and headshots received and formatted. | Speakers
Rehearsal schedule | Jenny Lee | In Progress | 2026-03-10 | High | Rescheduled from 2026-03-01 due to venue conflict. | Speakers
Dietary and accessibility needs | Jenny Lee | Done | 2026-03-05 | High | Tom Hartley: peanut allergy. Priya Desai: wheelchair access. Ben Okafor: gluten-free. | Speakers
Green room setup | Mike Chen | Not Started | 2026-03-19 | Medium | Setup morning of event. Includes refreshments and charging stations. | Speakers
Sponsors
Gold sponsors outreach | Tom Rodriguez | Done | 2026-01-15 | High | All 3 Gold slots filled. | Sponsors
Silver sponsors | Tom Rodriguez | Done | 2026-02-28 | Medium | All 7 Silver slots filled. Hooli declined. | Sponsors
Sponsor deliverables (logos) | Tom Rodriguez | Done | 2026-03-01 | Medium | All sponsor logos received and submitted to print. | Sponsors
Sponsor swag bags | Alex Johnson | Done | 2026-03-10 | Low | 350 bags prepared. Reused prior year tote bags from storage. | Sponsors
Sponsor booth layout | Mike Chen | Done | 2026-03-12 | Medium | Finalized with venue floor plan. 10 booths in foyer. | Sponsors
Marketing
Launch email | Alex Johnson | Done | 2026-01-20 | High | Sent to 2400 subscribers. 32% open rate. | Marketing
Website updates | Alex Johnson | Done | 2026-02-05 | Medium | Landing page live with full agenda and speaker bios. | Marketing
Social push schedule | Alex Johnson | In Progress | 2026-03-20 | Medium | Posting Monday/Wednesday/Friday. Copy in shared doc. | Marketing
Press release | Alex Johnson | Done | 2026-02-28 | Medium | Distributed via PRWire. 6 industry outlets picked it up. | Marketing
Print programs | Alex Johnson | Done | 2026-02-25 | Medium | 400 programs printed. | Marketing
Email reminders (T-7, T-3, T-1) | Alex Johnson | Done | 2026-03-14 | High | All three reminders scheduled in Mailchimp. | Marketing
Post-event survey | Alex Johnson | Not Started | 2026-03-22 | Low | Typeform template ready. | Marketing
Tech and AV
Registration app | Mike Chen | Done | 2026-02-10 | High | Live at registration.horizonsummit.com. | Tech
Badge printing setup | Mike Chen | Done | 2026-02-28 | High | Zebra printer loaned from office. | Tech
WiFi check | Mike Chen | Done | 2026-03-01 | High | Venue WiFi tested. Backup hotspot secured. | Tech
Session recording | Mike Chen | Done | 2026-03-15 | Medium | StreamCo selected. Contract signed. | Tech
Live streaming | Mike Chen | In Progress | 2026-03-20 | High | Platform confirmed (StreamCo). Testing scheduled 2026-03-19. | Tech
Slack channel for attendees | Alex Johnson | Done | 2026-02-05 | Low | Channel live. Invite in confirmation email. | Tech
Operations
Order giveaway t-shirts | Alex Johnson | Done | 2026-02-15 | Medium | 200 shirts ordered. Sizes S, M, L, XL. | Marketing
Confirm photographer | Sarah Kim | Done | 2026-02-18 | Medium | Deena Patel at LensCo. $2800 contract. | Marketing
Budget check with Finance | Sarah Kim | Done | 2026-03-12 | High | Current spend $87000 of $120000 budget. On track. | Finance

## Venue
Item | Status | Contact | Email | Notes
Marriott Bay — Main Hall | Booked | Diana Vance | dvance@marriott.com | Capacity 350. Deposit $5000 paid 2026-02-16.
Breakout Room A | Booked | Diana Vance | dvance@marriott.com | Capacity 60.
Breakout Room B | Booked | Diana Vance | dvance@marriott.com | Capacity 40.
Breakout Room C | Booked | Diana Vance | dvance@marriott.com | Capacity 30. Third track confirmed.
Catering (Marriott in-house) | Confirmed | Luis Hernandez | lhernandez@marriott.com | Option B: Mediterranean. Vegetarian track included.
Parking Lot A | Confirmed | Diana Vance | dvance@marriott.com | 180 spots.
Parking Lot B (overflow) | Confirmed | Mark Alvarez | malvarez@cityparking.com | 120 spots. Separate contract with City Parking Authority.
Loading dock access | Confirmed | Diana Vance | dvance@marriott.com | Available 6am–10am day of event.
Event WiFi | Confirmed | Venue IT | venueit@marriott.com | Dedicated 1 Gbps line. Backup hotspot secured.

## Speakers
Speaker | Company | Talk title | Status | Travel | Dietary | Email
Alicia Wu | Horizon | The Future of Ops (keynote) | Confirmed | Local | None | alicia@horizon.co
Raj Mehta | Databridge | Bridging Data Silos in 2026 | Confirmed | SFO → SEA | Vegetarian | raj.mehta@databridge.io
Priya Desai | Lumafy | Scaling Data Teams | Confirmed | BOS → SEA | Wheelchair access required | priya@lumafy.com
Rickard Hansson | Greycroft | What VCs Watch For in 2026 | Confirmed | NYC → SEA | Peanut allergy | tom@greycroft.vc
Jordan Li | Independent | Panel: AI and Workflow | Confirmed | Local | None | jordan.li@gmail.com
Sam Okonkwo | Northwind | Panel: AI and Workflow | Confirmed | Local | None | s.okonkwo@northwind.co
Lena Park | Orbital | Lightning: 5 Tools We Love | Confirmed | Local | None | lena@orbital.app
Ben Okafor | OpenForge | Lightning: OSS Patterns | Confirmed | Local | Gluten-free | ben@openforge.org

## Sponsors
Sponsor | Tier | Amount | Signed | Paid | Contact | Email | Notes
Acme Corp | Gold | 25000 | Yes | Paid | Karen Mitchell | karen.mitchell@acme.com | Returning sponsor
Globex | Gold | 25000 | Yes | Paid | Jim O'Brien | jobrien@globex.com | Returning sponsor
Initech | Gold | 25000 | Yes | Paid | Peter Gibbons | pgibbons@initech.com
Soylent Inc | Silver | 10000 | Yes | Paid | Miles Sanchez | msanchez@soylent.com
Massive Dynamic | Silver | 10000 | Yes | Paid | Nina Sharp | nsharp@massivedynamic.com
Umbrella | Silver | 10000 | Yes | Paid | Albert Wesker | awesker@umbrella.co
Stark Industries | Silver | 10000 | Yes | Paid | Pepper Potts | potts@stark.com
Wayne Enterprises | Silver | 10000 | Yes | Paid | Lucius Fox | lfox@wayne.com
Hooli | Silver | 10000 | Declined | N/A | N/A |  | Passed on 2026 sponsorship
Pied Piper | Silver | 10000 | Yes | Paid | Richard Hendricks | richard@piedpiper.com
Cyberdyne | Bronze | 5000 | Yes | Paid | Miles Dyson | mdyson@cyberdyne.com
Tyrell Corp | Bronze | 5000 | Yes | Paid | Eldon Tyrell | etyrell@tyrellcorp.com
Confirmed total |  | 145000
Committed total (all tiers) |  | 155000

## Budget
Category | Budgeted | Spent | Remaining | Notes
Venue | 45000 | 42000 | 3000 | Includes catering (Option B, Mediterranean).
Speakers (travel and fees) | 25000 | 22500 | 2500 | 8 speakers. Average $2800 per speaker.
Marketing | 15000 | 13200 | 1800 | Email, social, print programs, launch collateral.
Tech and AV | 18000 | 16500 | 1500 | StreamCo recording contract included.
Swag | 8000 | 7200 | 800 | 200 t-shirts and 350 tote bags.
Photography | 4000 | 2800 | 1200 | Deena Patel at LensCo.
Contingency | 5000 | 0 | 5000 | Reserved for day-of issues.
TOTAL | 120000 | 104200 | 15800

## Reference
Constant | Value | Notes
Tax rate | 8.5% | WA state sales tax
Service charge | 22% | Venue service charge
Per-person catering | 125 | Marriott banquet rate
Average flight cost | 650 | Per speaker
Average hotel per night | 280 | Per speaker